## Slide 1: CS223: Software Engineering
Software Development Processes

## Slide 2: Recap
Software engineering as a bridge between customer and developer
Different misconceptions about software developments
Legacy software
Software developments phases

## Slide 3: Objective
After the end of the class students should be able to
  State professional responsibilities of a software engineer
  Explain the need of software processes
  Describe ETVX model
  Differentiate between different properties of software processes

## Slide 5: What is a software process?
A set of ordered tasks to produce indented output of some kind
  Involving activates,
  Constraints; and
  Resources
The process of building a software product
  Life cycle
    Describes the life of the software from conception through
      implementation,
      delivery,
      use and
      maintenance.

## Slide 6: Component Software Processes
Two major processes
  Development
    focuses on development and quality steps needed to engineer the software
  Project management
    focuses on planning and controlling the development process
Development process is the heart of software process; other processes revolve around it
These are executed by different people
  Developers execute engineering process
  Project manager executes the management processes

## Slide 7: Component Processes…
Other processes
  Configuration management process
    manages the evolution of artifacts
  Change management process
    how changes are incorporated
  Process management process
    management of processes themselves
  Inspection process
    How inspections are conducted on artifacts

## Slide 8: Process Specification
Process is generally a set of phases
Each phase performs a well defined task and produces an output
Intermediate outputs – work products
At top level, typically few phases in a process
How to perform a particular phase
  Methodologies have been proposed

## Slide 9: ETVX Specification
ETVX approach to specify a step
  Entry criteria: conditions to be satisfied for initiating this phase
  Task: what is to be done in this phase
  Verification: the checks done on the outputs of this phase
  eXit criteria: when can this phase be considered done successfully
A phase also produces info for management

## Slide 10: ETVX approach
A
B
C
D

## Slide 11: Desired Process Properties
Provide high quality and productivity (Q & P)
Support testability as testing is the most expensive task
  Testing can consume 30 to 50% of total development effort
Support maintainability
  Maintenance can be more expensive than development;
  Over life up to 80% of total cost
Remove defects early
  As cost of removing defects increases with latency

## Slide 12: High Q&P: Early Defect Removal…
Cost of a defect increases with latency
Fixing a defect in operation can cost a 100 times the cost of fixing it in requirements itself
For high Q&P, the process must support early defect removal
That is why there is a V in ETVX, and quality control tasks in the software process

## Slide 13: Early Defect Removal…

## Slide 14: Desired Properties…
Predictability and repeatability
  Process should repeat its performance when used on different projects
    Outcome of using a process should be predictable
  Past performance can be used to predict future performance
  Without predictability, cannot estimate, or say anything about quality or productivity

## Slide 15: Predictability…
Predictable process is said to be under statistical control
  Repeatedly using the process produces similar results
  Results – properties of interest like quality, productivity, …
To consistently develop software with high Q&P
  Process must be in control

## Slide 16: Predictability…
Expected value of the property
Allowable error bound

## Slide 17: Support Change
Software changes for various reasons
Requirements change is a key reason
Requirement changes cannot be wished away or treated as “bad”
They must be accommodated in the process for software development

## Slide 18: Software Project
Project
  To build a software system within cost
  Schedule and with high quality which satisfies the customer
Project goals – high Q and high P
Suitable process needed to reach goals
For a project
  The process to be followed is specified during planning

## Slide 19: Projects Process
If a project chooses a model
  It will generally tailor it to suit the project
This produces the spec for the projects process
This process can then be followed in the project
Process is what is actually executed
Process specification is plan about what should be executed
Process model is a generic process specification
Many models have been proposed for the development process

## Slide 20: Development Process
A set of phases and each phase being a sequence of steps
Sequence of steps for a phase - methodologies for that phase.
Why have phases
  To employ divide and conquer
  Each phase handles a different part of the problem
  Helps in continuous validation

## Slide 21: Development Process
Commonly has these activities:
  Requirements analysis, architecture,
  Design, coding,
  Testing, delivery
Different models perform them in different manner

## Slide 22: Generic software process models
The waterfall model
  Separate and distinct phases of specification and development.
Evolutionary development
  Specification, development and validation are interleaved.
Component-based software engineering
  The system is assembled from existing components.

## Slide 23: Waterfall Model
Linear sequence of stages/ phases
Requirements – HLD – DD – Code – Test – Deploy
A phase starts only when the previous has completed
  No feedback
The phases partition the project
  Each addressing a separate concern

## Slide 24
Flow of Waterfall Model

## Slide 25: Properties of Waterfall Model
Linear ordering implies each phase should have some output
The output must be validated/certified
Outputs of earlier phases: work products
Common outputs of a waterfall:
  SRS, project plan, design docs, test plan and reports, final code, supporting docs

## Slide 26: Waterfall Advantages
Conceptually simple
  Cleanly divides the problem into distinct phases
  Phases can be performed independently
Natural approach for problem solving
Easy to administer in a contractual setup
Each phase is a milestone

## Slide 27: Waterfall disadvantages
Assumes that requirements can be specified and frozen early
May fix hardware and other technologies too early
Follows the “big bang” approach
  All or nothing delivery
  Too risky
Requirement bloating
Very document oriented
  Requiring docs at the end of each phase

## Slide 28: Waterfall Usage
Has been used widely
Well suited for projects where
  Requirements can be understood easily
  Technology decisions are easy
For familiar type of projects it still may be the most optimum

## Slide 29: Prototyping
It addresses the requirement specification limitation of waterfall
Do not finalize requirements only by discussions
A prototype is built to understand the requirements
Helps reduce the requirements risk
A small waterfall model replaces the requirements stage

## Slide 30: Prototyping: Typical flow

## Slide 31: Developing A Prototype
Starts with initial requirements
Only key features which need better understanding are included in prototype
No point in including those features that are well understood
Feedback from users taken to improve the understanding of the requirements

## Slide 32: How to minimize the cost?
Build only features needing clarification
“Quick and dirty”
  Quality not important, scripting etc. can be used
Things like exception handling, recovery, standards are omitted
Cost can be a few % of the total
Learning in prototype building will help in
  Building the software
  Besides improved requirements

## Slide 33: Pros and Cons of Prototyping
Advantages:
  Requirement will be more stable
  Requirement frozen later
  Experience helps in the main development
Disadvantages:
  Potential hit on cost and schedule
Applicability:
  When requirements are hard to elicit
  Confidence in requirements is low
    Requirements are not well understood

## Slide 34: Iterative Development
Counters the “all or nothing” drawback of the waterfall model
Combines benefit of prototyping and waterfall
Develop and deliver software in increments
Each increment is complete in itself
Can be viewed as a sequence of waterfalls
Feedback from one iteration is used in the future iterations

## Slide 35: Typical Flow of Iterative Enhancement

## Slide 36: Iterative delivery approach

## Slide 37: Properties of Iterative Development
Products almost always follow it
Used commonly in customized development also
  Businesses want quick response for software
  Cannot afford the risk of all-or-nothing
Newer approaches like XP, Agile,… all rely on iterative development

## Slide 38: Pros and Cons of Iterative Development
Benefits:
  Get-as-you-pay
  Feedback for improvement,
Drawbacks:
  Architecture/ design may not be optimal,
  Rework may increase, total cost may be more
Applicability:
  Response time is important, risk of long projects cannot be taken,
  All requirements are not known

## Slide 39: Timeboxing
Iterative is linear sequence of iterations
Each iteration is a mini waterfall
  Decide the specs, then plan the iteration
Time boxing
  Fix an iteration duration, then determine the specs
Divide iteration in a few equal stages
Use pipelining concepts to execute iterations in parallel

## Slide 40: Time Boxed Iterations
General iterative development
  Fix the functionality for each iteration,
  Then plan and execute it
In time boxed iterations
  Fix the duration of iteration
  Adjust the functionality to fit it
Completion time is fixed
  The functionality to be delivered is flexible

## Slide 41: Characteristics of Time boxed Iteration
This itself very useful in many situations
Has predictable delivery times
Overall product release and marketing can be better planned
Makes time a non-negotiable parameter and helps focus attention on schedule
Prevents requirements bloating
Overall development time is still unchanged

## Slide 42: Timeboxing – Taking Time Boxed Iterations Further
What if we have multiple iterations executing in parallel
Can reduce the average completion time by exploiting parallelism
For parallel execution,
  Can borrow pipelining concepts from hardware
This leads to Timeboxing Process Model

## Slide 43: Timeboxing Model – Basics
Development is done iteratively in fixed duration time boxes
Each time box divided in fixed stages
Each stage performs a clearly defined task that can be done independently
Each stage approximately equal in duration
There is a dedicated team for each stage
When one stage team finishes, it hands over the project to the next team

## Slide 44: Properties of Timeboxing
With this type of time boxes,
  Can use pipelining to reduce cycle time
Like hardware pipelining
  View each iteration as an instruction
As stages have dedicated teams
Simultaneous execution of different iterations is possible

## Slide 45: Example
An iteration with three stages – Analysis, Build, Deploy
  These stages are approximately equal in many situations
  Can adjust durations by determining the boundaries suitably
  Can adjust duration by adjusting the team size for each stage
Have separate teams for A, B, and D

## Slide 46: Pipelined Execution
AT starts executing it-1
AT finishes, hands over it-1 to BT, starts executing it-2
AT finishes it-2, hands over to BT; BT finishes it-1, hands over to DT; AT starts it-3, BT starts it-2 (and DT, it-1)

## Slide 47: Timeboxing Execution

## Slide 48: Timeboxing execution
First iteration finishes at time T
Second finishes at T+T/3; third at T+2 T/3, and so on
In steady state, delivery every T/3 time
If T is 3 weeks, first delivery after 3 weeks, 2nd after 4 weeks, 3rd after 5 weeks,…
In linear execution, delivery times will be 3 weeks, 6 weeks, 9 weeks,…

## Slide 49: Timeboxing execution
Duration of each iteration still the same
Total work done in a time box is also the same
Productivity of a time box is same
Yet, average cycle time or delivery time has reduced to a third

## Slide 50: Team Size
In linear execution of iterations, the same team performs all stages
If each stage has a team of S, in linear execution the team size is S
In pipelined execution, the team size is three times (one for each stage)
The total team size in timeboxing is larger; and this reduces cycle time

## Slide 51: Tasks of different teams

## Slide 52: Timeboxing
Advantages:
  Shortened delivery times,
  Other advantages of iterative, distributed execution
Disadvantages:
  Larger teams,
  Project management is harder,
  High synchronization needed, CM is harder
Applicability:
  When short delivery times very important
  Architecture is stable
  Flexibility in feature grouping

## Slide 53: Summary – Waterfall
Strength | Weakness | Types of Projects
Simple Easy to execute Intuitive and logical Easy contractually | All or nothing – too risky Requirements are frozen early May chose outdated hardware/tech Disallows changes No feedback from users Encourages req bloating | Well understood problems, Short duration projects, Automation of existing manual systems

## Slide 54: Summary – Prototyping
Strength | Weakness | Types of Projects
Helps requirement elicitation Reduces risk Better and more stable final system | Front heavy Possibly higher cost and schedule Encourages requirement bloating Disallows later change | Systems with novice users Areas with requirement uncertainty. Heavy reporting based systems can benefit from UI proto

## Slide 55: Summary – Iterative
Strength | Weakness | Types of Projects
Regular deliveries, leading to biz benefit Can accommodate changes naturally Allows user feedback Avoids requirement bloating Naturally prioritizes requirement Allows reasonable exit points Reduces risks | Overhead of planning each iteration Total cost may increase System arch and design may suffer Rework may increase | For businesses where time is imp; risk of long projects cannot be taken; req not known and evolve with time

## Slide 56: Summary – Timeboxing
Strength | Weakness | Types of Projects
All benefits of iterative Planning for iterations somewhat easier Very short delivery times | PM becomes more complex Team size is larger Complicated – lapses can lead to losses | Where very short delivery times are very important Where flexibility in grouping features Arch is stable

## Slide 57: Thank you
Next : Requirement Engineering